## Dependencies
Group | Item | Tasks |  | Deliverables | Assumptions | Task Dependencies
[6 empty] | Platform | Code Repository | Raw Asset Data | Data Cleaning Plan | Updated Project Scope | Cleaned Asset Data | UKCP18 Data | Hydrology Model(s) | Public Demonstrator Consultation | Representative Synthetic Data | Developed Asset Availability Models | Deployed Asset Availabiliy Models | Developed system model | Deployed System Model | Containerised information management Toolkit | Deployed information management Toolkit | Higher Quality Asset Data | Semantic Improvement Evaluation | Integration Architecture | Integration Architecture Evaluation | MVP Backend | MVP UI Wireframe | MVP UI
[6 empty] | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status | Status
[6 empty] | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date
A | 1 | A.1 | Set up platform on DAFNI servers | Platform |  | -
A | 2 | A.2 | Set up code repository and CI pipeline | Code Repository |  | X | -
B | 1 | B.1 | Define public demonstrator specifications | Public Demonstrator Specifications | [9 empty] | -
C | 1 | C.1 | Load UKCP18 and elevation data onto platform | UKCP18 Data |  | X | [5 empty] | -
C | 2 | C.2 | Load flood model onto platform | Hydrology Model(s) |  | X | [6 empty] | X
|  | C.3 | Refactor HiPIMS flood model | Flood model | [8 empty] | -
D | 1 | D.1 | Load raw data onto platform: Water | Raw Asset Data: Water |  | X |  | -
D | 2 | D.2 | Load raw data onto platform: Comms | Raw Asset Data: Comms |  | X |  | -
D | 3 | D.3 | Load raw data onto platform: Power | Raw Asset Data: Power |  | X |  | -
E | 1 | E.1 | Review raw data against project scope | Updated Project Scope |  | X | X | X |  | -
F | 1 | F.1 | Containerise information management tools | Containerised information management Toolkit |  |  | X | [12 empty] | -
F | 2 | F.2 | Deploy information management tools on platform | Deployed information management Toolkit |  | X | X | [12 empty] | X | -
F | 3 | F.3 | Semantic improvement | Higher Quality Asset Data |  | X | X | X | [13 empty] | -
G | 1 | G.1 | Develop data cleaning plan | Data Cleaning Plan |  | X | X | X | - | X
G | 2 | G.2 | Clean asset data: Water | Cleaned Asset Data: Water |  | X | X | X | X | X | -
G | 3 | G.3 | Clean asset data: Comms | Cleaned Asset Data: Comms |  | X | X | X | X | X | -
G | 4 | G.4 | Clean asset data: Power | Cleaned Asset Data: Power |  | X | X | X | X | X | -
H | 1 | H.1 | Expert elicitation: Water | Asset Availability Model: Water |  | X | X | X | Optional | X | X |  |  | X |  | -
H | 2 | H.2 | Expert elicitation: Comms | Asset Availability Model: Comms |  | X | X | X | Optional | X | X |  |  | X |  | -
H | 3 | H.3 | Expert elicitation: Power | Asset Availability Model: Power |  | X | X | X | Optional | X | X |  |  | X |  | -
H | 4 | H.4 | Load asset availability models onto platform | Deployed Asset Availability Models |  | X | X |  |  |  | X | X | X | X |  | X | -
I | 1 | I.1 | Develop OR / system model | System Model |  | X | X |  |  | X | X | X | X | X |  | X |  | -
I | 2 | I.2 | Load System model onto platform | Deployed System Model |  | X | X |  |  |  | X | X | X | X |  |  | X | X | -
J | 1 | J.1 | Data synthesis | Representative Synthetic Data |  | X | X |  |  | X | X |  |  | X | -
K | 1 | K.1 | Deploy integration architecture | Integration Architecture |  | X | X |  |  |  | X | X | X |  |  |  | X |  | X |  |  |  |  | -
L | 1 | L.1 | Evaluate semantic improvement benefits | Semantic Improvement Evaluation |  | X | X |  |  | X | X | X | X |  | Optional |  | X |  | X |  |  | X | -
L | 2 | L.2 | Evaluate integration architecture benefits | Integration Architecture Evaluation |  | X | X |  |  | X | X | X | X |  | Optional |  | X |  | X |  |  | Optional |  | X | -
M | 1 | M.1 | End-to-end integration | MVP Backend |  | X | X |  |  | X | X | X | X |  |  |  | X |  | X |  |  | Optional |  | Optional |  | -
M | 2 | M.2 | Gather technical visualisation requirements | MVP UI Wireframe |  | X | [20 empty] | -
M | 3 | M.3 | Develop technical visualisation | MVP UI |  | X | X | [18 empty] | X | X | -
N | 1 | N.1 | Decision support analysis | Risk/Confidence Understanding | [7 empty] | X | X